GSMP Images, Digital & Electronic Assets (IDEAs) Standards Maintenance Group (SMG)​
Report Date: Q2 2025
              Project Lead: David Buckley
Business purpose
Process all maintenance Work Requests for GS1 standards and guidelines related to digital assets (images, videos, 360-degree images, 3D, etc.) This group will act as a pool of experts for creation, storage, sharing, quality, implementation guidance, exchange and naming of digital assets and coordinate with associated Mission Specific Work Groups and other Standards Maintenance Groups.
Stakeholders
SDL	David Buckley
CE/Sol Liaison	Open
SME	Elsa Braz
AG Liaison	open
Chairs	Georgette Suggs (Sitation), / Patricia Thibaudet (Nestle France)
Last 90 days
Major work effort to simplify and reorganise the GS1 Product Image Standard (e.g., secondary images vs primary image ‘styles’).
Ongoing processing of GSMP work requests on the GS1 Product Image Specification Standard.
Addressing divergences in product image use.
Risks
Lack feedback on standard usage (e.g., GS1 Product Video Standard, quick reference guides, etc.)
Next 90 days
Publish the approved updates to the GS1 Product Image Standards.
Processing WR to merge GS1 Product Image Standards and Product Image Sharing/Delivery Guideline.
Risks
Meta Data use with images. Some users have already adopted, others happy with existing “legacy” solution. Impacts 1 image for multiple products/GTINs in particular.

---
GSMP Images, Digital & Electronic Assets (IDEAs) Standards Maintenance Group (SMG) (2 of 2)
Publication deliverables	Work Request Activity by year for Q1-3	Top Work request submitters
1	GS1 Product Image Specifications, 4.5	Sep 2025
2	GS1 Product Image Specifications, 4.4	Apr 2024
3	GS1 Product Video Standard, 1.0	Apr 2024
4	GS1 Mobile Ready Hero Images Guideline, 2.2	Feb 2024
Submitter	Number of WR
GS1 Germany	2
GS1 France	1
New risks (scope and resources) identified	No	Change request included	No
Legend	Complete	Not Started	On Time	Risk of being late	Change needed (not recoverable)